## Slide 1: Team OCTAVE
Chatbot with Customizable Voice
Sivaavanish K
Satish Kumar V K Siva Sathwik Srinivas R Kesavan M

## Slide 2: Overall Plan

## Slide 3: Detailed Schedule
# | Task | Owner | Start Date | End Date | Dependencies
1. | Training the chatbot with the input dataset | Sivaavanish | 6-10-21 | 6-10-21 | RASA,Python
2. | Deploying the chatbot model in Cloud | Sathwik | 7-10-21 | 7-10-21 | GCP
3. | Designed a web page to access the model | Satish | 7-10-21 | 8-10-21 | 
4. | Integrating the chatbot | Srinivas | 8-10-21 | 9-10-21 | 
5. | Displaying the messages in the webpage | Kesavan | 9-10-21 | 9-10-21 | 
6. | Testing the Chatbot by having a interactive conversation | Srinivas | 9-10-21 | 10-10-21 | 
7. | To generate a Voice dataset with 3 different voices. | Satish | 10-10-21 | 10-10-21 | 
8. | Training the model with the Voice Dataset | Sathwik | 11-10-21 | 11-10-21 | RASA
9. | Experimenting the Voice-bot in the webpage in different voices. | Kesavan | 12-10-21 | 12-10-21 | 
10. | Executing and documenting the entire application | Sivaavanish | 13-10-21 | 13-10-21 | 

## Slide 4: Risks & Mitigation / Action plan
# | Risk | Severity | Probability | Mitigation / Action Plan
1. | Miscommunication and Poor time estimates | High | Low | Updating team members with frequent meetings along with the project progress.
2. | Server Downtime | Medium | Medium | Performing periodic checks in the server to ensure stability
3. | Absence of Leadership | Medium | Low | Assigned a co-leader to take charge in the absence of leader in the time of unanticipated events